الجمهورية اللبنانية

الاسم والشهرة:--------------------

رقم المرشح :----------------------

وزارة التربية والتعليم العالي

المديرية العامة للتعليم المهني والتقني

===============				      الامتحانات الرسمية لشهادة الامتياز الفني

لدورة عام 2014 الأولى

الاختصاص والرمز     : المعلوماتية الادارية (23106-24007)

المادة                     : البحث العملاني											المعدل: (8 )

المستندات المسموح بها : آلة حاسبة غير مبرمجة										 المدة  : ساعة ونصف

Traiter les questions suivantes

- Maximiser la fonction économique suivante :

Z  = 2X1 +X2 + 3X3

Sous les contraintes:

X1 – 2X2 + 3X3  	= 12

2X1 + X2             	≥ 10

X2  - X3               	≤ 5

X1 , X2 , X3        	≥ 0

(8pts)

- Déterminer le plus court et le plus long chemin entre les nœuds (A) à (F) dans le graphique ci-dessous en utilisant l'algorithme de Ford

D

F

E

A

B

C

Les longueurs  entre les nœuds sont :

Arc  A – B  = 5	Arc  A – C = 2	Arc  B – E = 8	Arc  B – D = 1	Arc  C – E = 12

Arc  C – D = 6	Arc  E – D = 2	Arc  E – F = 1	Arc  D – E = 4 	Arc  D – F = 3

(4pts)

- La mise en exploitation d’un nouveau gisement minier demande la réalisation d’un certain nombre de tâches. Ces différentes tâches, ainsi que les tâches antérieures et leurs durées sont définies dans le tableau suivant :

| Tâches | Durée (en jours) | Tâche(s) antérieure(s) |
| --- | --- | --- |
| A | 7 | - |
| B | 3 | - |
| C | 4 | A |
| D | 2 | A , B |
| E | 8 | B |
| F | 6 | D , E |
| G | 5 | E |
| H | 7 | C , F |
| I | 5 | F , G |
| J | 3 | H , I |

- Déterminer les niveaux des tâches.

- Représenter ce projet par un diagramme PERT.

- Calculer les dates de démarrage au plus tôt et au plus tard de chaque tâche.

- Déterminer le chemin critique et les tâches critiques.

- Calculer la durée minimale de son exécution.

(8pts)

الجمهورية اللبنانية

الاسم والشهرة:--------------------

رقم المرشح :----------------------

وزارة التربية والتعليم العالي

المديرية العامة للتعليم المهني والتقني

===============				      الامتحانات الرسمية لشهادة الامتياز الفني

لدورة عام 2014 الأولى

الاختصاص والرمز     : المعلوماتية الادارية (23106-24007)

المادة                     : البحث العملاني											المعدل: (8 )

المستندات المسموح بها : آلة حاسبة غير مبرمجة										 المدة  : ساعة ونصف

Answer the following questions:

- Maximize  the following economical function:

Z  = 2X1 +X2 + 3X3

Under the constraints:

X1 – 2X2 + 3X3  	= 12

2X1 + X2          	≥ 10

X2  -  X3             	≤5

X1 , X2 , X3        	≥ 0

(8pts)

- Determine the shortest and the longest path between nodes (A) to (F) in the below graph using the algorithm of Ford

D

F

E

A

B

C

The lengths between the nodes are:

Arc  A – B  = 5	Arc  A – C = 2	Arc  B – E = 8	Arc  B – D = 1	Arc  C – E = 12

Arc  C – D = 6	Arc  E – D = 2	Arc  E – F = 1	Arc  D – E = 4 	Arc  D – F = 3

(4pts)

- The exploitation of a new mineral deposit requires the completion of a number of tasks. These different tasks,  as well as the immediate predecessors and their durations are defined in the following table:

| Tasks | Duration (in days) | Immediate predecessor(s) |
| --- | --- | --- |
| A | 7 | - |
| B | 3 | - |
| C | 4 | A |
| D | 2 | A , B |
| E | 8 | B |
| F | 6 | D , E |
| G | 5 | E |
| H | 7 | C , F |
| I | 5 | F , G |
| J | 3 | H , I |

- Determine the levels of tasks.

- Represent this project by a PERT network.

- Calculate the earliest and the latest occurrence time of each task.

- Determine the critical path and the critical tasks.

- Calculate the minimal duration of  its execution

(8pts)